Implementation at a glance

Behavioral Targeting and Intelligence: what each side does, and what we need from you

Tapestry, launch brand Coach   ·   v1.0   ·   18 September 2026   ·   Confidential

Your pages send events. We return decisions addressed by your own identifiers. Your front end renders, always, and renders your default when there is no decision.

## The steps

| Step | We do | You do |
| --- | --- | --- |
| 1. Design | Run the registry, taxonomy and slot sessions. Audit your content sample. | Data science, content operations and a front-end lead in the room. Send 100 to 500 assets. |
| 2. Environment | Provision your lower environment, issue keys and console accounts. | Send the origins. Run our connection check from inside your network. |
| 3. Data | Register your content, calibrate tagging with you, connect the product feed. | Content export or feed credentials. Product feed. Lifecycle and rights fields. |
| 4. Instrumentation | Ship the SDK and tag plan. Verify events end to end. | Install the SDK, emit events, wire consent, sign the login assertion, run QA. |
| 5. Placement | Configure slots, weights, pins and defaults. | Render by your identifiers. A default per slot. Your timeout. |
| 6. Verification | Build the end-to-end run and drive it once. | Re-run it yourselves, and agree what you saw. |
| 7. Launch | Production environment, alerting, runbook, support, tuning. | Security and privacy sign-off. Holdout and metric. Release slot. Tuning owner. |

## What we need from you

| Area | What | Step |
| --- | --- | --- |
| Content | Every eligible asset: a stable identifier that survives republish, a type, tags, the slots it may fill, a render reference, lifecycle dates. | 1, then 3 |
| Products | Feed and attribute vocabulary. The identifiers your events use. Attributes travel on events and sort requests. | 3 |
| Pages | Slot map: stable slot identifiers, item counts, what is off limits, a default for every slot. | 1 |
| Events | Content impression, click, dwell, video complete. Product view, add to cart, wishlist. Order completed, with value. | 4 |
| Identity, consent | One backend endpoint that signs a short-lived assertion at login. Your consent framework and its withheld behavior. | 4 |
| Network, privacy | Origins per environment, script and connect allow-listing, socket egress through your delivery network and firewall. Retention per category. Nothing inbound, no ports. | 2 |
| Measurement | Primary metric written down. Holdout share approved before the first personalized page. | 7 |
| People | Registry approver, content owner, front-end lead, backend owner, security approver, QA, tuning owner. | 1 |

## The five that move the date

- Stable content identifiers and the export. Nothing starts without them.

- Data layer maturity. The largest single variable in the instrumentation effort.

- Socket egress through your delivery network and firewall. Cheap now, expensive in December.

- Front-end capacity before your code freeze. The critical path runs through your developers.

- Security review booked early, with a named approver.